Volunteer Recruiting Timeline

December 2025

- All TB Captains identified

- Distribute TB2025 SignUp to Captains for updates/ changes (slots ID’d, descriptions, times, # of volunteers wanted)

- Request changes returned to Connie by 1/6/2026

January 2026

- Upgrade the SignUp Genius app (pay for Silver on a month-to-month basis)

- Create TB2026 SignUp incorporating changes from captains

- 1/10  send TB2026 SignUp to Captains for Final Review

- Send names/emails of TB2025 volunteers to Captains (for recruiting)

- Meet with TB Director to review volunteers requested

- 1/15 TB2026 SignUp sent to elist

Feb-April 2026

- Distribute reports to Captains as requested

- Send emails to elist identifying volunteers needed

- Maintain TB2026 SignUp (make changes as requested)

May 2026

- Cancel SignUp Genius Silver

- Create copy of TB2026 (saving data)

Volunteer Picnic

December 2025

- Select date for picnic (Saturday, May2?)

- Work with TB Director to determine type of picnic (catered, pizza, burgers, themed, etc) and budget

January 2026

- Reserve location for picnic (typically a SJ Park)

- Populate TB2026 SignUp Genius with picnic volunteers needed (will be dependent on type of picnic)

Feb- March

- Depending on picnic type selected, research caterers and/or plan menu

April 2026

- 4/15 send email to volunteers asking them to rsvp if they plan to attend the volunteer picnic

- Pickup TB leftovers (bars/cookies/sodas/fruit, etc) on April 26

- Go to TB shed (day after TB when shed is being restocked) to pick up what’s needed for picnic (April 27)

- Shop for needed non-perishable products (sodas, paper goods, etc)

May

- Depending on picnic type, buy food

- Setup picnic site

- Return ACTC material to shed